## Sheet1
|  | Optimistic Effort P Hours | Most Likely Effort P Hours | Pessimistic Effort P Hours | Actual Effort | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Status
Login Page |  | 0 |  | 0
Design | Design Development | 5 | 6 | 9 |  | 2020-06-11 | 2020-06-11 |  |  | Completed
Design Review | Design Review | 4 | 5 | 8 |  | 2020-06-11 | 2020-06-11 |  |  | Completed
Design Rework | Design Rework | 3 | 4 | 6 |  | 2020-06-12 | 2020-06-12 |  |  | Completed
Data Access Layer Development | Code Development | 4 | 5 | 8 |  | 2020-06-12 | 2020-06-15 |  |  | Completed
Business Layer Development | Code Development | 5 | 7 | 11 |  | 2020-06-15 | 2020-06-15 |  |  | Ongoing
Service Layer Development | Code Development | 6 | 8 | 12 |  | 2020-06-15 | 2020-06-16 |  |  | Ongoing
Web Client Development | Code Development | 6 | 8 | 12 |  | 2020-06-16 | 2020-06-17 |  |  | Ongoing
Unit Test | Dev Testing | 6 | 8 | 12 |  | 2020-06-18 | 2020-06-18
Code Review | Code Review | 4 | 5 | 8 |  | 2020-06-19 | 2020-06-19
Code Rework | Code Rework | 4 | 5 | 8 |  | 2020-06-19 | 2020-06-19
|  | 0 |  | 0
Customer Registration Page |  | 0 |  | 0
Design | Design Development | 3 | 4 | 6 |  | 2020-06-22 | 2020-06-23
Design Review | Design Review | 3 | 4 | 6 |  | 2020-06-23 | 2020-06-23
Design Rework | Design Rework | 4 | 5 | 8 |  | 2020-06-24 | 2020-06-24
Data Access Layer Development | Code Development | 4 | 5 | 8 |  | 2020-06-24 | 2020-06-25
Business Layer Development | Code Development | 5 | 6 | 9 |  | 2020-06-25 | 2020-06-26
Service Layer Development | Code Development | 6 | 8 | 12 |  | 2020-06-26 | 2020-06-29
Web Client Development | Code Development | 8 | 10 | 15 |  | 2020-06-29 | 2020-06-30
Unit Test | Dev Testing | 4 | 5 | 8
Code Review | Code Review | 3 | 4 | 6
Code Rework | Code Rework | 4 | 5 | 8
|  | 0 |  | 0
Product List Page |  | 0 |  | 0
Design | Design Development | 3 | 4 | 6
Design Review | Design Review | 3 | 4 | 6
Design Rework | Design Rework | 3 | 4 | 6
Data Access Layer Development | Code Development | 4 | 5 | 8
Business Layer Development | Code Development | 4 | 5 | 8
Service Layer Development | Code Development | 4 | 5 | 8
Web Client Development | Code Development | 12 | 16 | 24
Unit Test | Dev Testing | 4 | 5 | 8
Code Review | Code Review | 4 | 5 | 8
Code Rework | Code Rework | 4 | 5 | 8
|  | 0 |  | 0
Product Cart Page |  | 0 |  | 0
Design | Design Development | 4 | 5 | 8
Design Review | Design Review | 3 | 4 | 6
Design Rework | Design Rework | 4 | 5 | 8
Web Client Development | Code Development | 6 | 8 | 12
Code Review | Code Review | 4 | 5 | 8
Code Rework | Code Rework | 4 | 5 | 8
|  | 0 |  | 0
Checkout Page |  | 0 | 0 | 0
Design | Design Development | 4 | 5 | 8
Design Review | Design Review | 3 | 4 | 6
Design Rework | Design Rework | 4 | 5 | 8
Data Access Layer Development | Code Development | 4 | 5 | 8
Business Layer Development | Code Development | 4 | 5 | 8
Service Layer Development | Code Development | 5 | 6 | 9
Web Client Development | Code Development | 6 | 8 | 12
Unit Test | Dev Testing | 3 | 4 | 6
Code Review | Code Review | 4 | 5 | 8
Code Rework | Code Rework | 4 | 5 | 8
|  | 0 |  | 0
Payment Confirmation Page |  | 0 |  | 0
Design | Design Development | 4 | 5 | 8
Design Review | Design Review | 3 | 4 | 6
Design Rework | Design Rework | 4 | 5 | 8
Data Access Layer Development | Code Development | 3 | 4 | 6
Business Layer Development | Code Development | 4 | 5 | 8
Service Layer Development | Code Development | 3 | 4 | 6
Web Client Development | Code Development | 5 | 6 | 9
Unit Test | Dev Testing | 5 | 6 | 9
Code Review | Code Review | 4 | 5 | 8
Code Rework | Code Rework | 4 | 5 | 8
|  | 0 |  | 0
Order Details Page |  | 0 |  | 0
Design | Design Development | 4 | 5 | 8
Design Review | Design Review | 3 | 4 | 6
Design Rework | Design Rework | 4 | 5 | 8
Data Access Layer Development | Code Development | 3 | 4 | 6
Business Layer Development | Code Development | 4 | 5 | 8
Service Layer Development | Code Development | 3 | 4 | 6
Web Client Development | Code Development | 5 | 6 | 9
Unit Test | Dev Testing | 5 | 6 | 9
Code Review | Code Review | 4 | 5 | 8
Code Rework | Code Rework | 4 | 5 | 8
|  | 0 |  | 0
Payment History Page |  | 0 |  | 0
Design | Design Development | 0 |  | 0
Design Review | Design Review | 0 |  | 0
Design Rework | Design Rework | 0 |  | 0
Data Access Layer Development | Code Development | 0 |  | 0
Business Layer Development | Code Development | 0 |  | 0
Service Layer Development | Code Development | 0 |  | 0
Web Client Development | Code Development | 0 |  | 0
Unit Test | Dev Testing | 0 |  | 0
Code Review | Code Review | 0 |  | 0
Code Rework | Code Rework | 0 |  | 0
|  | 0 |  | 0
Database Development |  | 0 |  | 0
Design | Design Development | 0 |  | 0
Design Review | Design Review | 0 |  | 0
Design Rework | Design Rework | 0 |  | 0
Database Development | Code Development | 0 |  | 0
Database Development Review | Design Review | 0 |  | 0
Database Development Rework | Design Rework | 0 |  | 0
Data Feed | Code Development | 0 |  | 0
|  | 0 |  | 0
General/Miscellaneous |  | 0 |  | 0
Environment Setup | Project Planning | 7 | 9 | 14 |  | 2020-06-03 | 2020-06-04
Requirement Analyze | Requirements Dev | 5 | 7 | 11 |  | 2020-06-09 | 2020-06-10
Requirement Review | Requirements Review | 4 | 5 | 8 |  | 2020-06-10 | 2020-06-10
Project Structure and Design | Code Development | 9 | 12 | 18 |  | 2020-06-10 | 2020-06-11
Database Integration Using EF | Code Development | 6 | 8 | 12 |  | 2020-06-12
Logging | Code Development | 0 |  | 0 |  | 2020-06-12
Exception | Code Development | 0 |  | 0 |  | 2020-06-12
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0